## Tracker
30-Minute-Per-Day Project Logger & Tracker
Project Name | Ecommerce Operations KPI Project |  |  | Completed Days | 0 |  | Progress Bar | ░░░░░░░░░░░░░░░░░░░░
Start Date | 05/04/2026 |  |  | Completion % | 0%
Planned Daily Minutes | 30 |  |  | Total Time Logged (mins) | 0
Planned Days | 35 |  |  | Days Remaining | 35
Update Status, Time Spent, Notes, and Key Output each day. Planned Date auto-fills from the Start Date.
Day # | Planned Date | Week | Planned Focus | Status | Time Spent (mins) | Started? | Done? | Notes | Key Output
1 | 2026-04-05 | 1 | Create folder structure, README.md, requirements.txt, and GitHub repo | Not Started |  | No | No
2 | 2026-04-06 | 1 | Download dataset and place it in /data; inspect file manually | Not Started |  | No | No
3 | 2026-04-07 | 1 | Open dataset in Python and print shape, columns, and first rows | Not Started |  | No | No
4 | 2026-04-08 | 1 | Check missing values, data types, cancellations, and negative quantities | Not Started |  | No | No
5 | 2026-04-09 | 1 | Define KPI list and business goal in README | Not Started |  | No | No
6 | 2026-04-10 | 1 | Start clean_data.py: load file, parse dates, create Revenue column | Not Started |  | No | No
7 | 2026-04-11 | 1 | Save first cleaned output and commit changes | Not Started |  | No | No
8 | 2026-04-12 | 2 | Identify cancelled orders and choose handling rule | Not Started |  | No | No
9 | 2026-04-13 | 2 | Handle invalid rows: prices, quantities, key missing fields | Not Started |  | No | No
10 | 2026-04-14 | 2 | Create month and year_month fields | Not Started |  | No | No
11 | 2026-04-15 | 2 | Check duplicates and comment code clearly | Not Started |  | No | No
12 | 2026-04-16 | 2 | Save cleaned CSV and document cleaning rules | Not Started |  | No | No
13 | 2026-04-17 | 2 | Re-run cleaning script from scratch and fix issues | Not Started |  | No | No
14 | 2026-04-18 | 2 | Push cleaned workflow to GitHub and update README | Not Started |  | No | No
15 | 2026-04-19 | 3 | Choose SQL setup and create database/table | Not Started |  | No | No
16 | 2026-04-20 | 3 | Load cleaned data into SQL and verify row count | Not Started |  | No | No
17 | 2026-04-21 | 3 | Write SQL query for total revenue and total orders | Not Started |  | No | No
18 | 2026-04-22 | 3 | Write SQL query for average order value and monthly revenue | Not Started |  | No | No
19 | 2026-04-23 | 3 | Write SQL query for top countries and top products | Not Started |  | No | No
20 | 2026-04-24 | 3 | Write SQL query for cancellations/returns analysis | Not Started |  | No | No
21 | 2026-04-25 | 3 | Test and tidy all SQL queries with comments | Not Started |  | No | No
22 | 2026-04-26 | 4 | Run KPI queries and collect outputs | Not Started |  | No | No
23 | 2026-04-27 | 4 | Choose 5–8 findings and draft analysis summary | Not Started |  | No | No
24 | 2026-04-28 | 4 | Create 1–2 simple charts in Python | Not Started |  | No | No
25 | 2026-04-29 | 4 | Save charts to docs/reports and reference them in README | Not Started |  | No | No
26 | 2026-04-30 | 4 | Write final_summary.md with findings and recommendations | Not Started |  | No | No
27 | 2026-05-01 | 4 | Improve README structure and repo walkthrough | Not Started |  | No | No
28 | 2026-05-02 | 4 | Review repo from recruiter perspective and tidy presentation | Not Started |  | No | No
29 | 2026-05-03 | 5 | Draft 3 CV bullet points from the project | Not Started |  | No | No
30 | 2026-05-04 | 5 | Write 30-second interview explanation of the project | Not Started |  | No | No
31 | 2026-05-05 | 5 | Write 60-second explanation covering dataset, cleaning, and insights | Not Started |  | No | No
32 | 2026-05-06 | 5 | Refactor Python code and clean filenames/folders | Not Started |  | No | No
33 | 2026-05-07 | 5 | Refine SQL naming and professionalism | Not Started |  | No | No
34 | 2026-05-08 | 5 | Add realistic future improvements section to README | Not Started |  | No | No
35 | 2026-05-09 | 5 | Final review: publish repo and add link to CV/LinkedIn draft | Not Started |  | No | No
Weekly Summary
Week | Planned Days | Completed Days | Completion % | Minutes Logged | Comment
1 | 7 | 0 | 0% | 0
2 | 7 | 0 | 0% | 0
3 | 7 | 0 | 0% | 0
4 | 7 | 0 | 0% | 0
5 | 7 | 0 | 0% | 0
Formulas:
Planned Date = IF(B3="","",B3+[Day #]-1)

## Instructions
How to use this tracker
1. Edit the blue input cells on the Tracker sheet: Project Name, Start Date, Planned Daily Minutes, Planned Days.
2. Each day, update Status, Time Spent (mins), Notes, and Key Output.
3. Keep the planned focus unless you intentionally change the day's task.
4. Status options: Not Started, In Progress, Completed, Blocked.
5. Summary metrics at the top update automatically.
6. Use the Weekly Summary section to review consistency and bottlenecks.
7. Recommended habit: at the end of each session, write one note on what to do next tomorrow.